## Website Rebuild Checklist - 7 S
| Steps | Sub Steps | Details | Your Answer | Assign Responsibilty To Person/s | Additional Notes
FALSE | 1. Content Audit
FALSE |  | Create a content audit spreadsheet | Content Audit Spreadsheet Included! See Second Tab Below
FALSE |  | Evaluate each piece of content on your current site
FALSE |  | Assign responsibilities
FALSE |  | Spot the gaps. | What's not on your current site but should be on the new one?
FALSE
FALSE | 2. Functionality Audit
FALSE |  | Make a list of functionality requirements that exist on your current site | ex: contact forms, event calendars, newsletter signups, maps, directories, or e-commerce tools
FALSE |  | Make a list of new functionality you want to include
FALSE
FALSE | 3. Clarify Design Goals
FALSE |  | What works and doesn't work about your current design? | Include examples and links to your current site
FALSE |  | Which websites do you admire? Save examples. | Add URLs to sites or pages you like. Try to be specific about what you like about them.
FALSE |  | Are there design styles you definitely want to avoid?
FALSE |  | Do you have brand guidelines with specific colors and fonts? | For some people this is a 25 page document, for others it's just a font or font-style preference.
FALSE
FALSE | 4. Identify Pain Points
FALSE |  | Why do you want a new website? Identify the driving factors behind the redesign.
FALSE |  | What about your current site actually works well? (Don't throw out what's already effective!)
FALSE |  | What specific issues frustrate you or your users? Note everything from outdated design to poor mobile experience.
FALSE |  | What feedback do you hear from customers about your website? Their perspective is invaluable.
FALSE |  | Are you happy with your current content management system (CMS) or page builder like Beaver Builder or Elementor? Technical limitations often drive redesigns.
FALSE
FALSE | 5. Create a Rough Budget |  | Having a range in mind helps guide conversations with potential web partners and ensures you get realistic recommendations.
FALSE
FALSE | 6. Consider SEO
FALSE |  | Are you keeping track of your current SEO performance? Benchmarking rankings, traffic, and conversions help you measure success.
FALSE |  | Will your URLs stay the same, or need redirects? Updating URLs without proper 301 redirects can break links and hurt rankings.
FALSE |  | How will you migrate content without losing search visibility? Key pages, metadata, and internal links need to be preserved.
FALSE |  | Are you using this opportunity to improve site speed and technical SEO? A website rebuild is a great time to optimize performance.
FALSE
FALSE | 7. Plan for Additional Resources
FALSE |  | Photography & visuals | Will you need professional photos, or will stock images work? If a shoot is required, schedule it early so designers can work with real images, not placeholders. If using real photos, professional photos are recommended with high resolution and take into consideration any elements that might be applicable (such as: a specific season to take the photo, event). It is important to think through what you would like represented on your website in advance in order not experience delays during the website design process.
FALSE |  | Content creation | Who will handle writing and editing? If multiple stakeholders are involved, plan for approval cycles.
FALSE |  | Timeline expectations | Most websites take at least 8 weeks, while larger projects can stretch to 6-8 months.
FALSE
FALSE
FALSE
Have Questions? Ready to Get Started? https://clockworkwd.com
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Website Content Audit
Content Type | Page/Post Name | State of Content | Link Add hyperlink to easily reference | Additional Notes | Assign Responsibilty To Person/s | New Site Status Use this column when new site build starts
ACCESS YOUR CURRENT SITE'S SITEMAP Delete This Row After Reading Note > |  |  |  | Tip: If your current site is on WordPress, try adding “/sitemap.xml” to the end of your main URL to find your websites’ sitemap. This may be helpful to look to get a snapshot of all of your current content.
Pages (5) (list how many here)
| Home | Needs Rewriting |  |  |  | Approved
| About Us | Needs Review
Services
| Careers | Needed but Doesn't Exist Yet
| Contact Us | Good - Use As Is
Posts (list how many here)
| Hello World | Delete - No Longer Needed
7 Tips for Aspiring List Makers
Custom Post Types (list how many here) These could be team members, events, portfolio items etc. Create a new "Content Type" group for each.
Custom Post Type Single Item